## PRN221_ClassCode_GroupName
Overall Project
Group Name: | Bee |  | Note : -
Max Mark :
Student Percent (%) | 100%
Teacher Percent (%) | 0%
No | Student ID | Student Name | Class Name | Student Percent | Teacher Percent (%) | Mark | Note
1 | SE170203 | Nguyễn Trung Hậu | NET1706 | 30% |  | #DIV/0!
2 | SE170355 | Nguyễn Nhật Hào | NET1706 | 27% |  | #DIV/0!
3 | SE170228 | Nguyễn Thụy Phúc Lộc | NET1706 | 23% |  | #DIV/0!
4 | SE173466 | Nguyễn Trung Kiên | NET1706 | 20% |  | #DIV/0!

## Group Tasks
Task List
No | Task Name | Percent (%) | Student Name | Created At | Updated At | Status | Note
1 | Database Design | 100% | Hậu, Lộc, Hào, Kiên | 2024-06-10 |  | Done
2 | ERD Conceptual | 100% | Hậu, Lộc, Hào, Kiên | 2024-06-10 |  | Done
3 | Code base | 100% | Hậu | 2024-06-11 |  | Done
4 | Login | 100% | Lộc | 2024-06-11 |  | Done
5 | Register Customer | 100% | Hậu | 2024-06-11 |  | Done
6 | View Clinics Page | 100% | Hậu | 2024-06-14 |  | Done
7 | View Service | 100% | Hậu | 2024-06-15 |  | Done
8 | Make appointment | 100% | Hậu | 2024-06-20 |  | Done
9 | View Appointment (history) | 100% | Hậu | 2024-06-20 |  | Done
10 | Reschedule Appointment | 100% | Hậu | 2024-06-21 |  | Done
11 | View Owner Clinic | 20% | Hào | 2024-06-15 |  | Done
12 | Register Clinic | 20% | Hào | 2024-06-15 |  | Done
13 | Register Dentist | 10% | Hào | 2024-06-20 |  | Proccess
14 | Register Dentist for service | 100% | Hào | 2024-06-20 |  | Proccess
15 | Cancel Appointment | 100% | Lộc |  |  | Done
16 | View Dashboard (Admin) | 100% | Lộc |  |  | Done
17 | Dentist update status appointment | 100% | Hậu | 2024-06-22 |  | Done
18 | Admin create service | 50% |  |  |  | Proccess
19 |  | 10% |  |  |  | Proccess
20 |  | 100% |  |  |  | Done
21 |  | 20% |  |  |  | Proccess
22 |  | 20% |  |  |  | Proccess
23 |  | 20% |  |  |  | Proccess
24 |  | 20% |  |  |  | Done